TARP-SPACE Phase 1 — Personal Agent Layer Architecture & Implementation Plan for Two Developers v1.0 · Confidential · March 2026

Objective: Build a standalone personal agent that onboards users through natural language, builds a per-transaction negotiation mandate, matches against seeded marketplace inventory, and explains results — with no live agent network required.

# 1. Overview & Guiding Principles

Phase 1 proves the core hypothesis: a mandate built through natural language conversation produces meaningfully better marketplace matches than keyword search. The entire system is designed to be useful to a single user on day one, before any network density exists.

Four principles govern all architecture and implementation decisions in this phase:

- Conversation-first, extraction-first. When a user states their need, the agent extracts every structured field it can before asking a single question. Questions only cover gaps.

- Mandate privacy is a hard gate, not a soft rule. No mandate parameter is ever exposed to the matching layer in raw form. A privacy gate validates every outbound signal before transmission.

- Explainability over accuracy. Every match result includes an agent-generated explanation. An imperfect match the user understands is more valuable than a perfect match they cannot verify.

- Observability from day one. Every mandate field change, match attempt, escalation, and accept/reject signal is logged as a structured event. This is the training data for every future improvement.

# 2. System Architecture

The Phase 1 system has five layers. Each layer has a single, clearly bounded responsibility. The LLM is only invoked in the Conversation and Explanation layers — never in matching, privacy enforcement, or data persistence.

| Layer | Responsibility | LLM Involved | Owner |
| --- | --- | --- | --- |
| 1 Conversation Layer | Natural language intake, extraction, gap-filling, mandate confirmation | Yes — Claude Sonnet | Dev A |
| 2 Mandate Layer | Schema validation, persistence, version history, completeness scoring, audit log | No | Dev A |
| 3 Privacy Gate | Hard enforcement of mandate privacy rules before any data leaves the mandate store | No — pure function | Dev B |
| 4 Matching Engine | Hard constraint filtering, semantic ranking, trust weighting, explainable scores | No | Dev B |
| 5 Explanation Layer | Agent-written per-match explanations and escalation questions | Yes — Claude Sonnet | Dev A |

## 2.1 Data Flow: User Request to Match Results

The following describes the end-to-end flow for a user expressing a new need:

| Step | Action | Detail |
| --- | --- | --- |
| 1 | User sends natural language message | "I'm looking for a mid-century modern couch under $500 in Montrose, needs to be pet-friendly" |
| 2 | Extraction pass (LLM) | Agent parses: intent=buy, vertical=goods, category=couch, style=mid-century modern, budget_ceiling=$500, location=Montrose, soft_pref=pet-friendly. Marks all fields as source=inferred |
| 3 | Gap analysis (rule-based) | System computes completeness score. Identifies unfilled high-priority fields: condition, timing, dealbreakers |
| 4 | Gap-filling questions (LLM, one at a time) | Agent asks only about highest-priority gap: "What condition are you looking for — does it need to be like-new, or is well-used fine?" |
| 5 | Mandate assembly | After all critical gaps filled, system assembles Mandate object. Completeness score computed. Agent reflects mandate back for confirmation |
| 6 | Owner confirmation | User confirms or corrects. Mandate version saved. Mandate marked active |
| 7 | Privacy gate | Gate validates mandate before passing sanitized signals to matching engine. No ranges, ceilings, or dealbreakers transmitted raw |
| 8 | Hard constraint filter | Matching engine eliminates all inventory records that violate hard constraints (location radius, category, budget ceiling) |
| 9 | Semantic ranking | Remaining results ranked by embedding similarity to mandate description + trust weight |
| 10 | Escalation check | Results outside mandate range but within configurable threshold flagged for escalation |
| 11 | Explanation generation (LLM) | For each top result, agent generates a plain-language explanation of the match |
| 12 | Results returned | Top N results with explanations, alignment scores, and escalation prompts where applicable |

## 2.2 Mandate Schema

The Mandate is the system of record for a user's per-transaction negotiation position. Every field carries a source flag (explicit or inferred) and a version number. The user can view and correct any field at any time.

| Field | Type | Description | Source |
| --- | --- | --- | --- |
| mandate_id | UUID | Unique identifier, system-generated | System |
| owner_id | UUID | Linked to verified user profile | System |
| intent_type | Enum | buy / sell / request_service / offer_service / discover | Extracted or elicited |
| vertical | Enum | goods / services | Extracted or elicited |
| category | String | furniture, plumbing, tutoring, etc. | Extracted or elicited |
| description | String | Natural language summary used for semantic matching | Generated post-extraction |
| hard_constraints | Array | Non-negotiable requirements — match fails if violated | Extracted or elicited |
| negotiation_range | Array | Floor, ceiling, opening position, flexibility score per dimension | Extracted or elicited |
| soft_preferences | Array | Optimize for, but not required — with relative weights | Extracted or inferred |
| dealbreakers | Array | Auto-disqualification conditions — never transmitted raw | Extracted or elicited |
| escalation_triggers | Array | Conditions where agent stops and asks owner | Elicited or defaulted |
| autonomy_level | Enum | supervised / escalate_key_points / fully_autonomous | Owner-set, default: escalate |
| completeness_score | Float 0–1 | Readiness to match. Must reach 0.7 before matching begins | Computed |
| version | Integer | All versions retained for audit and refinement feedback | System |
| source_flags | Map<field, source> | explicit / inferred per field — auditable and correctable | System |

## 2.3 Extraction & Gap-Filling Logic

The extraction pass is the most critical performance surface in the system. It determines how many questions the agent must ask before matching can begin. A high-quality extraction pass means 0–2 questions for a well-specified input. A poor one means 8+ questions and user drop-off.

Design Rule: Extract first. Ask only about gaps. Never ask about a field the user has already provided — even implicitly. If the user says 'under $500', the ceiling is extracted as $500 and the floor defaults to $0.

| Dimension | Priority | Extraction Signal Examples | Default If Not Provided |
| --- | --- | --- | --- |
| intent_type | 1 — Critical | "I'm looking for", "selling", "need someone to" | buy (if browsing context) |
| vertical | 2 — Critical | Category mention implies vertical | goods |
| category | 3 — Critical | "couch", "plumber", "guitar lessons" | None — must ask |
| budget / price | 4 — High | "under $500", "around $400", "$300–$600" | None — must ask |
| location | 5 — High | "in Montrose", "near me", "77006" | User profile location |
| condition / quality | 6 — Medium | "like-new", "well-used is fine", "professional" | Any (no constraint) |
| timing | 7 — Medium | "this weekend", "ASAP", "no rush" | Flexible |
| style / aesthetic | 8 — Low | "mid-century modern", "minimalist", "experienced" | No preference |
| dealbreakers | 9 — Low | "no particle board", "must have receipt" | None |
| autonomy level | 10 — Low | Never extracted — always explicitly set by owner | escalate_key_points |

## 2.4 Completeness Score Computation

The completeness score is a weighted average of filled mandate dimensions. The agent does not enter the matching phase until the score reaches 0.7. Critical fields have higher weights.

| Field Group | Weight | Score Contribution if Filled |
| --- | --- | --- |
| intent_type + vertical + category | 0.35 | 0.35 |
| budget / price range | 0.20 | 0.20 |
| location | 0.15 | 0.15 |
| condition / timing | 0.15 | 0.15 (0.075 each) |
| soft preferences (1+) | 0.10 | 0.10 |
| dealbreakers (0+ is ok) | 0.05 | 0.05 |
| Total at full completion | 1.00 | 1.00 |

## 2.5 Privacy Gate

The privacy gate is a stateless validation function that runs before any mandate data is passed to the matching engine. It is not an LLM instruction — it is a rule-enforced code layer.

| Rule | Enforcement | Severity |
| --- | --- | --- |
| Ceiling / floor of negotiation_range never transmitted as a range | Stripped to current position + directional signal only | Critical |
| Dealbreakers never transmitted to counterparty or matching engine in raw form | Evaluated locally; matching engine receives boolean: constraint_satisfied=true/false | Critical |
| Hard constraints never exposed — only satisfaction boolean | Same pattern as dealbreakers | Critical |
| Opening position must not equal ceiling or floor | Validation check on mandate before activation | High |
| Location fuzzing in all pre-match queries | Exact location only revealed post-introduction with mutual consent | Medium |

## 2.6 Matching Engine

Phase 1 matching is against a static seeded inventory — no live agent-to-agent negotiation. The engine runs three stages sequentially:

| # | Stage | Logic |
| --- | --- | --- |
| 1 | Hard Constraint Filter | Eliminates any inventory record that violates a hard constraint. Category mismatch, location outside radius, price above ceiling. This stage is deterministic and fast — no embeddings, no scoring. Returns the surviving candidate set. |
| 2 | Semantic Ranking | Generates embedding from mandate.description. Computes cosine similarity against pre-computed listing embeddings. Applies trust weight multiplier per result (community overlap, past transaction edges). Produces a ranked list with alignment score per result. |
| 3 | Escalation Flagging | Results within a configurable threshold above mandate ceiling (e.g. within 15%) are flagged for escalation rather than filtered. Agent generates a specific yes/no question for each escalation candidate: "This listing is at $520 — $20 above your ceiling. Want me to explore it?" |

## 2.7 Feedback & Mandate Refinement Loop

Every accept/reject signal from the user is a training event. The system uses these signals to update inferred fields and improve future extraction accuracy.

| User Signal | System Action | Mandate Update |
| --- | --- | --- |
| Accepts a result | Mark result as accepted. Log mandate_id, result_id, aligned dimensions | Inferred soft_preferences reinforced. Completeness score stable |
| Rejects a result with reason | Log rejection reason. Extract new constraint from reason text | New dealbreaker or hard_constraint added with source=inferred. Completeness score updated |
| Rejects without reason | Log rejection. No immediate mandate change | Pattern detection after 3+ rejections of same attribute type triggers refinement prompt |
| Answers escalation question yes | Proceed with exploration. Log flexibility signal | negotiation_range ceiling updated by escalation delta with source=inferred |
| Answers escalation question no | Dismiss result. Reinforce ceiling boundary | Hard constraint on price tightened. Escalation threshold may be reduced |
| Explicitly corrects mandate field | Immediately update field. Re-run matching | Field updated, source changed to explicit. Version incremented |

# 3. API Design

All services communicate over a RESTful HTTP API with a single backend (FastAPI). WebSocket is used only for real-time chat streaming. The API is designed so the frontend never touches mandate internals directly — all mutations go through the Conversation Layer or explicit Mandate API endpoints.

## 3.1 Core Endpoints

| Method | Endpoint | Description | Owner |
| --- | --- | --- | --- |
| POST | /api/v1/conversations | Create a new conversation session. Returns session_id and initial agent greeting | Dev A |
| POST | /api/v1/conversations/{id}/messages | Send user message. Returns agent response (streaming supported via SSE). Triggers extraction pass internally | Dev A |
| GET | /api/v1/mandates/{mandate_id} | Retrieve full mandate with source flags and version history | Dev A |
| PATCH | /api/v1/mandates/{mandate_id} | Owner explicitly updates one or more mandate fields. Triggers version increment and re-scoring | Dev A |
| POST | /api/v1/mandates/{mandate_id}/confirm | Owner explicitly confirms mandate. Activates mandate for matching | Dev A |
| GET | /api/v1/mandates/{mandate_id}/history | Full version history for audit interface | Dev A |
| POST | /api/v1/mandates/{mandate_id}/search | Trigger a match search against seeded inventory. Returns ranked results with scores and explanations | Dev B |
| POST | /api/v1/mandates/{mandate_id}/signals | Submit accept/reject signal for a result. Triggers refinement loop | Dev B |
| GET | /api/v1/inventory | List seeded inventory with filters (admin/ops use for seeding) | Dev B |
| POST | /api/v1/inventory | Add a new listing to seeded inventory (admin/ops) | Dev B |
| GET | /api/v1/agents/{owner_id}/activity | Full activity log for a user's agent — all searches, matches, escalations | Dev B |

## 3.2 Key Request/Response Shapes

POST /conversations/{id}/messages — Request

{ "message": "I want a mid-century couch under $500 in Montrose", "session_id": "uuid" }

POST /conversations/{id}/messages — Response

{ "agent_message": "Got it — mid-century modern couch in Montrose for under $500. What condition are you looking for?", "mandate_delta": { "category": "couch", "style": "mid-century modern", "budget_ceiling": 500, "location": "Montrose" }, "completeness_score": 0.55, "gaps_remaining": ["condition", "timing"], "ready_to_match": false }

POST /mandates/{id}/search — Response

{ "results": [ { "listing_id": "uuid", "alignment_score": 0.91, "price": 420, "within_mandate": true, "explanation": "Strong match: mid-century style confirmed in listing photos, like-new condition, 0.4mi from Montrose center, $80 below your ceiling.", "matched_dimensions": ["style", "condition", "location", "price"], "escalation": null }, { "listing_id": "uuid2", "alignment_score": 0.72, "price": 560, "within_mandate": false, "escalation": { "question": "This listing is $60 above your ceiling but matches perfectly on style and condition. Explore it?", "threshold_delta": 60 } } ], "search_id": "uuid", "mandate_version": 3 }

# 4. Database Schema

All data lives in PostgreSQL 16 with pgvector. No additional infrastructure. The schema is designed to be Neo4j-compatible for the trust graph when Phase 2 requires multi-hop queries.

| Table | Purpose | Key Columns | Owner |
| --- | --- | --- | --- |
| users | Identity and profile | id, email, name, location_raw, location_geom, verified_at, autonomy_default | Dev A |
| mandates | Current mandate per transaction | id, owner_id, intent_type, vertical, category, description, completeness_score, autonomy_level, is_active, version | Dev A |
| mandate_fields | Per-field storage with source tracking | mandate_id, field_name, field_value (jsonb), source (explicit/inferred), created_at, version | Dev A |
| mandate_versions | Full version snapshots for audit | mandate_id, version, snapshot (jsonb), changed_fields, changed_by, created_at | Dev A |
| conversations | Conversation session metadata | id, owner_id, mandate_id, created_at, last_message_at, status | Dev A |
| messages | Individual messages per conversation | id, conversation_id, role (user/agent), content, mandate_delta (jsonb), created_at | Dev A |
| inventory | Seeded marketplace listings | id, category, vertical, description, price, condition, location_geom, seller_id, metadata (jsonb), embedding (vector) | Dev B |
| search_runs | Each matching run against inventory | id, mandate_id, mandate_version, created_at, result_count, top_score | Dev B |
| search_results | Individual results per search run | id, search_run_id, listing_id, alignment_score, within_mandate, explanation, matched_dimensions (jsonb), escalation (jsonb) | Dev B |
| signals | Accept/reject feedback events | id, owner_id, search_result_id, signal_type, reason, mandate_delta_applied (jsonb), created_at | Dev B |
| activity_log | Structured event log for all agent actions | id, owner_id, mandate_id, event_type, payload (jsonb), created_at | Dev B |
| trust_edges (Phase 2 ready) | Graph adjacency table, Neo4j-compatible schema | from_user_id, to_user_id, edge_type, weight, source, created_at, expires_at | Dev B |

# 5. LLM Call Discipline

Unconstrained LLM usage will make the system economically unviable at scale. The LLM is only called in two places: the Conversation Layer (extraction + gap-filling) and the Explanation Layer (result explanations). Matching, privacy enforcement, and data persistence are entirely LLM-free.

| LLM Call | Context Budget | Output Budget | Trigger | Frequency |
| --- | --- | --- | --- | --- |
| Extraction pass | 600 tokens (user message + mandate schema + extraction prompt) | 400 tokens (structured JSON delta) | Every user message in active mandate build | Once per message |
| Gap question generation | 400 tokens (gap list + conversation history last 3 turns) | 200 tokens (single question) | When completeness < 0.7 and gaps remain | Once per gap |
| Mandate reflection generation | 500 tokens (assembled mandate) | 350 tokens (plain-language summary) | When completeness reaches 0.7, before confirmation | Once per mandate |
| Match explanation generation | 700 tokens (listing metadata + mandate summary + matched dimensions) | 400 tokens (plain-language explanation) | Per result in top N (max 5) | Up to 5x per search |
| Escalation question generation | 400 tokens (listing delta + mandate boundary) | 200 tokens (specific yes/no question) | Per escalation-flagged result | 0–3x per search |

Cost Alert: Alert when per-user LLM cost exceeds $0.05/month. This is the leading indicator of runaway context or unnecessary LLM calls. Two LLM calls per message is the maximum in normal operation.

# 6. Implementation Plan

The work is split between two developers across four two-week sprints. The split is designed so that Dev A (Conversation & Mandate) and Dev B (Matching & Infrastructure) can work in parallel with a single clean integration boundary: the Mandate API.

Integration Contract: Dev A owns the Mandate object and Conversation API. Dev B owns everything downstream of a confirmed mandate. The integration boundary is POST /mandates/{id}/search — Dev B consumes a confirmed mandate; Dev A produces it. This boundary must be agreed and mocked on Day 1.

## 6.1 Developer Responsibilities

| Dev A — Conversation & Mandate. - Conversation Layer (extraction, gap-filling, confirmation). - Mandate schema, CRUD, version history, completeness scoring. - Mandate audit interface (view, edit, source flags). - Explanation Layer (match explanations, escalation questions). - Conversation UI (chat interface, mandate build progress). - Mandate review UI (field-by-field audit view). | Dev B — Matching & Infrastructure. - Postgres schema, migrations, pgvector setup. - Privacy Gate (hard enforcement, event logging). - Seeded inventory ingestion + embedding pipeline. - Matching Engine (hard filter, semantic rank, escalation flag). - Feedback/signal processing and mandate refinement loop. - Activity log, search history UI, dev infrastructure (CI/CD, env). |
| --- | --- |

## 6.2 Sprint Plan

| Sprint 1 | Weeks 1–2 | Foundation — Schema, Infrastructure, Integration Contract |
| --- | --- | --- |

| Task | Developer | Detail | Done When |
| --- | --- | --- | --- |
| Database schema v1 | Dev B | All tables, indexes, pgvector extension, migrations. trust_edges table included (Phase 2 ready) | Schema applied to dev + staging; migration script tested |
| Mock Mandate API | Dev A | Stub all mandate endpoints returning hardcoded JSON. Dev B unblocked immediately | Dev B can call POST /search against a mock confirmed mandate |
| FastAPI project setup | Dev B | Repo structure, environments, Dockerfile, CI pipeline, DigitalOcean staging deploy | Both devs can deploy to staging from main branch |
| Extraction prompt v1 | Dev A | System prompt + few-shot examples for extraction pass. Validated against 20 handcrafted test inputs | Extraction pass correctly fills 80%+ of fields on well-specified inputs |
| Inventory ingestion script | Dev B | Script to load 50+ seeded Houston furniture listings with metadata. Embedding generation via Claude or OpenAI embeddings | 50 listings queryable in staging DB with embeddings populated |
| Auth integration | Dev A | Supabase Auth — user creation, JWT verification middleware, owner_id propagation | Protected endpoints reject unauthenticated requests |
| Week 2 integration checkpoint | Both | Dev A's real Mandate API replaces mocks. Dev B's search endpoint called against real mandate | End-to-end: user message → mandate built → search called → raw results returned |

| Sprint 2 | Weeks 3–4 | Core Loop — Conversation, Matching, Explanation |
| --- | --- | --- |

| Task | Developer | Detail | Done When |
| --- | --- | --- | --- |
| Full extraction + gap-filling loop | Dev A | Multi-turn conversation: extract → score → ask gap question → re-extract → confirm. Completeness score visible per turn | User can go from raw message to completeness 0.7+ in ≤4 exchanges on standard inputs |
| Privacy Gate implementation | Dev B | Pure function. All 3 critical privacy rules enforced. Logs every decision as privacy_gate_event. Integrated into /search before matching | Privacy gate blocks a test mandate with exposed ceiling. Event logged correctly |
| Hard constraint filter | Dev B | Category, location radius (PostGIS), price ceiling. Deterministic. Fast (target: <100ms on 500 listings) | Filter eliminates correct listings in unit tests. Query time <100ms |
| Semantic ranking | Dev B | pgvector cosine similarity. mandate.description embedding vs. listing embeddings. Returns ranked list with scores | Top results for test mandates match expected listings. Similarity scores sensible |
| Mandate confirmation UI | Dev A | Chat interface renders mandate delta inline. Completeness progress bar. Confirm button activates mandate | User can confirm mandate from chat UI. Mandate marked active in DB |
| Explanation generation | Dev A | LLM call per result (max 5). Prompt: listing metadata + mandate summary + matched dimensions → plain-language explanation | Explanations accurate and specific. No hallucinated attributes |
| Escalation flag + question | Dev A + Dev B | Dev B flags results within 15% of ceiling. Dev A generates specific yes/no question per flag | Escalation results display with question. Yes/no response logged as signal |

| Sprint 3 | Weeks 5–6 | Feedback Loop, Audit Interface, Activity Log |
| --- | --- | --- |

| Task | Developer | Detail | Done When |
| --- | --- | --- | --- |
| Mandate refinement loop | Dev A + Dev B | Accept/reject signals trigger mandate_delta computation. Dev B processes signal; Dev A updates inferred mandate fields. Version incremented | Repeated rejections of same attribute type trigger refinement prompt in chat |
| Mandate audit view | Dev A | Full mandate displayed field by field. Source badge (explicit / inferred) per field. Edit inline. Version history accessible | User can view, edit, and see history of every mandate field |
| Agent activity log UI | Dev B | Chronological feed of every search, match, escalation, signal, mandate update. Filterable by mandate | User can see full agent history. Each event links to relevant mandate version |
| Trust weight integration | Dev B | community_overlap and past_transaction edges factored into ranking score multiplier. Seeded with manual trust data for Phase 1 test cohort | Trust-weighted results differ from non-weighted baseline. Difference logged |
| Autonomy level configuration | Dev A | Owner sets autonomy per mandate from UI. Default: escalate_key_points. Fully autonomous requires unlock (not available Phase 1) | Autonomy level persisted per mandate. Supervised mode shows confirmation prompt before each search |
| Observability events | Dev B | All 10 required event types from PRD firing correctly. Structured JSON to stdout + persisted to activity_log | All event types confirmed in staging logs during end-to-end test run |

| Sprint 4 | Weeks 7–8 | Polish, Performance, Phase 1 Exit Criteria |
| --- | --- | --- |

| Task | Developer | Detail | Done When |
| --- | --- | --- | --- |
| Performance hardening | Dev B | End-to-end match latency target: <4s p95. Query plan review on inventory search. pgvector index tuning (IVFFlat) | Load test: 100 concurrent searches in <4s p95 |
| Mobile-responsive UI | Dev A | Agent console and chat interface fully functional on mobile. Push notification wiring for match alerts | All core flows usable on iOS Safari. Push notification fires on new match |
| Extraction regression suite | Dev A | 50 test cases covering edge inputs, ambiguous language, partial specs. Automated on CI | CI fails if extraction accuracy drops below 80% on test suite |
| Privacy gate penetration test | Dev B | Manual test: attempt to extract mandate range, ceiling, and dealbreakers via API manipulation and prompt injection | Zero leakage confirmed. All attack vectors blocked and logged |
| Cohort onboarding | Both | Onboard first 20 internal test users. Instrument mandate completeness, match acceptance, D7 retention | 20 users with active mandates. At least 15 have received match results |
| Phase 1 exit metric review | Both | Match acceptance rate, D7 retention, mandate completeness score distribution | Acceptance >30%, D7 retention >40%, completeness >0.7 for 80% of mandates |

# 7. Observability Events

Every event below must fire correctly before Phase 1 exits. These events are the training data for Phase 2 matching improvements and the RLHF feedback pipeline.

| Event Type | Required Fields | Owner |
| --- | --- | --- |
| mandate_created | owner_id, mandate_id, vertical, completeness_score, autonomy_level | Dev A |
| mandate_updated | mandate_id, field_changed, old_value, new_value, source (explicit/inferred) | Dev A |
| extraction_completed | mandate_id, message_id, fields_extracted, fields_remaining, completeness_score, latency_ms | Dev A |
| mandate_confirmed | mandate_id, completeness_score, version, confirmed_at | Dev A |
| search_started | mandate_id, mandate_version, search_id | Dev B |
| privacy_gate_decision | mandate_id, field, action (pass/strip/block), rule_applied | Dev B |
| search_completed | search_id, mandate_id, candidate_count_pre_filter, candidate_count_post_filter, top_score, latency_ms | Dev B |
| escalation_triggered | search_id, result_id, listing_id, threshold_delta, question_text | Dev A + Dev B |
| signal_received | owner_id, search_result_id, signal_type, reason, mandate_delta_applied | Dev B |
| mandate_refined | mandate_id, field_changed, trigger_signal_id, old_value, new_value | Dev B |

# 8. Phase 1 Exit Criteria

Phase 1 is complete when all of the following are measurably true with real users from the founding cohort:

| Criterion | Target | Measurement |
| --- | --- | --- |
| Mandate completeness score | > 0.7 for 80% of completed onboardings | mandate_created events, completeness_score distribution |
| Match acceptance rate | > 30% | signal_received events, signal_type=accept ratio |
| D7 retention (post first match) | > 40% | Users returning to app within 7 days of first match result |
| Extraction accuracy | > 80% of fields correctly extracted on well-specified inputs | Automated test suite pass rate on CI |
| End-to-end match latency | < 4s p95 | search_completed events, latency_ms distribution |
| Privacy incidents | 0 | privacy_gate_decision events, action=block count (should be 0 for legitimate mandates) |
| Mandate refinement loop active | Measurably improving match quality within sessions | Accept rate on re-searches after refinement vs. first search |

Phase 2 Dependency: The agent-to-agent negotiation protocol must be fully designed and reviewed before Phase 2 implementation begins — not after. This design work should be assigned during Sprint 4 of Phase 1, so protocol review can happen in parallel with Phase 1 polish.

# 9. Risk Register

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Extraction quality too low — users answer too many questions, drop off during mandate build | Medium | High | Invest Sprint 1–2 in extraction prompt quality. Measure avg questions-to-0.7 completeness. Target ≤3 questions for well-specified inputs. Iterate prompt before external users | Dev A |
| Privacy gate too aggressive — strips too much mandate signal, matches degrade | Low | Medium | Privacy gate is rule-based, not heuristic. Rules are explicit and testable. Add a 'gate audit' mode in staging that logs strip decisions without blocking | Dev B |
| Seeded inventory too thin — matching produces obvious or repeated results | High | High | 50 listings minimum before any external user onboarded. Verify embedding diversity before launch. Flag if top-3 results are always same listing | Dev B |
| LLM explanation hallucination — agent explains a match with attributes not in listing | Medium | Medium | Explanation prompt strictly grounded: only reference fields present in listing metadata. Add post-generation validation against listing schema | Dev A |
| Mandate refinement loop over-corrects — one rejection narrows mandate too aggressively | Medium | Medium | Single rejection does not update mandate. Pattern detection requires 3+ consistent rejections. All inferred updates surfaced to user for explicit confirmation before applying | Dev A + Dev B |
| Integration friction between Dev A and Dev B — blocked waiting for each other | Medium | High | Mock Mandate API on Day 1. Weekly integration checkpoint. Shared Postman/OpenAPI contract committed to repo on Day 1 | Both |

Tarp-Space Phase 1  ·  Personal Agent Layer  ·  Architecture & Implementation Plan  ·  v1.0  ·  Confidential  ·  March 2026